PROJECT EXECUTIVE SUMMARY

Enterprise CRM Migration -- Salesforce to HubSpot

Status: ON TRACK  |  Phase 2 of 3  |  Executive Steering Committee  |  April 2026

PROJECT OVERVIEW

This project migrates Meridian Corp's sales and marketing CRM from Salesforce Enterprise to HubSpot Sales Hub Enterprise. The migration affects 340 users across Sales, Marketing, Customer Success, and Partnerships. Scope includes data migration, integration re-wiring (ERP, billing, support), and user training. Budget: $410,000. Timeline: 9 months (Jan-Sep 2026).

CURRENT STATUS

| Overall Health | GREEN -- On track |
| --- | --- |
| Budget Status | GREEN -- $187K spent of $410K (46%); on budget |
| Schedule Status | GREEN -- Phase 2 complete on target (April 30 milestone) |
| Scope | YELLOW -- One scope addition pending: mobile app integration (est. +$22K, +2 weeks) |
| Risk Level | LOW-MEDIUM -- Data mapping complexity higher than estimated; mitigation in place |

ACCOMPLISHMENTS THIS PERIOD (MAR-APR 2026)

Completed full Salesforce data export and validation (4.2M contacts, 87K deals, 18 months activity history).

HubSpot sandbox environment provisioned and configured with all custom properties mapped.

ERP (NetSuite) integration tested successfully in sandbox; 99.7% data fidelity on 500-record test batch.

Phase 2 user acceptance testing completed by Sales leadership team (42 users); 3 minor UI feedback items logged.

NEXT PERIOD PLAN (MAY-JUN 2026)

Execute production data migration (May 15-16 maintenance window).

Launch HubSpot for Sales and Marketing teams; Salesforce read-only for 30-day parallel run.

Complete Customer Success user training (80 users, 3 sessions).

Resolve mobile integration scope decision with IT leadership by May 10.

KEY RISKS AND MITIGATIONS

| Risk | Probability | Impact | Mitigation |
| --- | --- | --- | --- |
| Data deduplication volume larger than scoped | Medium | High | Brought in HubSpot PS consultant; 2-week buffer in schedule |
| Salesforce parallel run extends beyond 30 days | Low | Medium | Executive mandate for cutover; cost structure incentivizes speed |
| Mobile integration delay | High | Low | Descoped to Phase 4 if decision not reached by May 10 |

DECISIONS REQUIRED

DECISION NEEDED (May 10): Approve mobile integration scope addition (+$22K, +2 weeks) or defer to Phase 4.

DECISION NEEDED (May 15): Confirm maintenance window for production migration (6-hour Saturday window).

Prepared by: Sarah Chen, Project Manager | s.chen@meridiancorp.com | (512) 555-0142