EXECUTIVE SUMMARY

Proposal: Community Health Navigation Program
City of Riverside -- Department of Public Health RFP #2026-PH-14

Submitted by: Riverside Community Health Alliance  |  April 18, 2026

PROPOSAL OVERVIEW

Riverside Community Health Alliance (RCHA) proposes a 24-month Community Health Navigation Program to address the City of Riverside's identified priority of reducing preventable emergency department utilization among uninsured and underinsured residents. RCHA requests $380,000 over two years to deploy six certified community health workers in the three highest-utilization zip codes.

PROBLEM STATEMENT

Riverside's three highest-utilization zip codes account for 38% of non-emergency ED visits at Riverside University Health System -- at an average cost of $2,100 per avoidable visit. The root cause is not health status but access: 67% of repeat ED utilizers do not have a primary care provider, and 44% cite did not know where else to go as their primary reason for ED use.

PROPOSED SOLUTION

Six full-time certified CHWs embedded in community settings (libraries, faith communities, community centers) rather than clinic-based, to reach residents before they are in crisis.

Structured care navigation protocol connecting each resident to a primary care medical home within 30 days of first contact.

Bi-directional data sharing with RUHS ED to identify and proactively outreach to repeat utilizers.

Peer support model: CHWs are residents of the target zip codes, sharing cultural and linguistic background with the population served.

ORGANIZATION QUALIFICATIONS

| Founded | 1997 -- 29 years serving Riverside County |
| --- | --- |
| Annual budget | $4.2M -- clean audits for past 5 years |
| Staff | 68 FTE, including 22 certified CHWs |
| Relevant experience | Managed 3 CHW programs totaling $2.1M for DHCS, achieving 94% deliverable completion |
| Key subcontractor | RUHS -- formal data-sharing MOU in place |

EXPECTED OUTCOMES

| Outcome | Year 1 Target | Year 2 Target |
| --- | --- | --- |
| Residents navigated to primary care | 350 | 650 (cumulative) |
| Reduction in repeat ED visits (program participants) | 20% | 32% |
| Estimated ED cost avoidance | $294K | $548K cumulative |
| CHW certification maintained | 100% | 100% |

Contact: Maria Flores, RCHA Executive Director, mflores@rchaonline.org, (951) 555-0198.