## Construction Schedule
Construction Project Schedule
Project name:
Site address:
Project manager:
Start date:
# | Task / Milestone | Responsible | Start Wk | Dur (wks) | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24
SITE PREPARATION
1 | Site clearing and grading | Contractor A | 1 | 2
2 | Temporary utilities | Utilities Co | 2 | 1
FOUNDATION
3 | Excavation | Excavator | 3 | 2
4 | Foundation pour | Concrete Co | 5 | 2
5 | Waterproofing | Contractor A | 7 | 1
FRAMING
6 | Floor framing | Framer | 7 | 2
7 | Wall framing | Framer | 9 | 3
8 | Roof framing | Framer | 11 | 2
ROUGH-IN MEP
9 | Plumbing rough-in | Plumber | 12 | 3
10 | Electrical rough-in | Electrician | 12 | 3
11 | HVAC rough-in | HVAC Co | 13 | 2
INSULATION AND DRYWALL
12 | Insulation | Contractor B | 15 | 2
13 | Drywall | Drywaller | 16 | 3
FINISHES
14 | Painting | Painter | 19 | 3
15 | Flooring | Flooring Co | 20 | 3
16 | Cabinetry and fixtures | Contractor B | 21 | 2
FINAL
17 | Final inspections | Inspector | 22 | 2
18 | Punch list | PM | 23 | 1
19 | Owner walkthrough | PM | 24 | 1