## Project Gantt
Project Gantt Chart
Project name:
Project manager:
Start date:
# | Phase / Task | Owner | Start Wk | Dur (wks) | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16
PHASE 1: INITIATION
1 | Project charter | PM | 1 | 1
2 | Stakeholder identification | PM | 1 | 1
PHASE 2: PLANNING
3 | Scope definition | BA | 2 | 2
4 | Resource plan | PM | 2 | 2
5 | Risk register | PM | 3 | 1
PHASE 3: EXECUTION
6 | Design | Designer | 4 | 3
7 | Backend development | Dev | 5 | 5
8 | Frontend development | Dev | 6 | 5
9 | Integration | Dev | 10 | 2
PHASE 4: MONITORING
10 | Testing and QA | QA | 11 | 3
11 | UAT | PM | 13 | 2
PHASE 5: CLOSURE
12 | Deployment | Dev | 14 | 2
13 | Documentation | Writer | 14 | 2
14 | Post-launch review | PM | 16 | 1