## Product Backlog
AGILE PROJECT PLAN — Product Backlog
Project: [Name] ¦ Product Owner: [Name] ¦ Last updated: [Date]
ID | User Story / Feature | Acceptance Criteria | Story Pts | Priority | Sprint | Status
US-001 | As a user I can log in with email and password | Correct creds = dashboard; bad creds = error msg | 3 | High | Sprint 1 | Done
US-002 | As a user I can reset my password via email | Reset link sent; expires in 1h | 2 | High | Sprint 1 | Done
US-003 | As a user I can view my profile page | Name, avatar, and email shown | 2 | Medium | Sprint 1 | In Progress
US-004 | As a user I can edit my profile information | Changes saved and reflected immediately | 3 | Medium | Sprint 2 | To Do
US-005 | As an admin I can view all user accounts | Paginated list with search | 5 | Medium | Sprint 2 | To Do
US-006 | As a user I can export data as CSV | Export button triggers download | 3 | Low | Sprint 3 | To Do
US-007 | As a user I receive email notifications | Opt-in; email arrives within 5 min | 5 | Low | Backlog | To Do
US-008 | As an admin I can deactivate user accounts | Deactivated user cannot log in | 2 | High | Sprint 2 | To Do

## Sprint Board
SPRINT BOARD — Active Sprint
Sprint #: [1] ¦ Goal: [Sprint goal] ¦ Dates: [Start] to [End]
ID | Task | Assignee | Pts | Status | Notes
US-001 | Implement login endpoint (backend) | [Dev A] | 2 | Done
US-001 | Build login form (frontend) | [Dev B] | 1 | Done
US-002 | Password reset email flow | [Dev A] | 2 | Done
US-003 | Profile page UI | [Dev B] | 2 | In Progress | Blocked: awaiting design
US-008 | Admin deactivate user API | [Dev A] | 1 | In Progress
US-008 | Admin deactivate user UI toggle | [Dev B] | 1 | To Do
VELOCITY SUMMARY
Total Points: | 9 | Completed: | 5 | Velocity %: