## Phases and Tasks
DETAILED PROJECT PLAN
Project: [Name] ¦ PM: [Name] |  |  |  |  | Start: [Date] ¦ End: [Date] ¦ Budget: $[Amount]
Status Codes: Complete In Progress Not Started Blocked
ID | Task / Deliverable | Start | End | Days | Owner | Status | Budget $ | Notes
PHASE 1 - INITIATION
1.1 | Stakeholder identification | 2026-06-10 | 2026-06-11 | 2 | [PM] | Not Started | 0
1.2 | Project charter sign-off | 2026-06-12 | 2026-06-13 | 2 | [PM] | Not Started | 500 | Requires exec approval
1.3 | Kick-off meeting | 2026-06-14 | 2026-06-14 | 1 | [PM] | Not Started | 200
PHASE 2 - PLANNING
2.1 | Requirements gathering | 2026-06-17 | 2026-06-21 | 5 | [BA] | Not Started | 2000
2.2 | Technical architecture design | 2026-06-22 | 2026-06-26 | 5 | [Tech] | Not Started | 3000
2.3 | Risk register | 2026-06-27 | 2026-06-28 | 2 | [PM] | Not Started | 0
2.4 | Procurement / vendor selection | 2026-06-29 | 2026-07-02 | 4 | [PM] | Not Started | 500
PHASE 3 - EXECUTION
3.1 | Development sprint 1 | 2026-07-05 | 2026-07-18 | 14 | [Dev] | Not Started | 12000
3.2 | Development sprint 2 | 2026-07-19 | 2026-08-01 | 14 | [Dev] | Not Started | 12000
3.3 | Design and UX | 2026-07-05 | 2026-07-25 | 21 | [UX] | Not Started | 5000 | Parallel with dev
PHASE 4 - TESTING
4.1 | QA / test case execution | 2026-08-04 | 2026-08-13 | 10 | [QA] | Not Started | 4000
4.2 | UAT with stakeholders | 2026-08-14 | 2026-08-18 | 5 | [PM] | Not Started | 1000
4.3 | Bug fixes and regression | 2026-08-19 | 2026-08-22 | 4 | [Dev] | Not Started | 3000
PHASE 5 - DEPLOYMENT
5.1 | Production deployment | 2026-08-25 | 2026-08-25 | 1 | [Dev] | Not Started | 500
5.2 | Post-launch monitoring (2 weeks) | 2026-08-26 | 2026-09-05 | 10 | [Dev] | Not Started | 2000
5.3 | Project closure report | 2026-09-06 | 2026-09-07 | 2 | [PM] | Not Started | 200

## Budget Summary
PROJECT BUDGET SUMMARY
Budget figures are indicative. Update with actual costs as project progresses.
Phase | Description | Budgeted $ | Actual $ | Variance $
Phase 1 | Initiation | 700
Phase 2 | Planning | 5500
Phase 3 | Execution | 29000
Phase 4 | Testing | 8000
Phase 5 | Deployment | 2700
Reserve | Contingency (10%) | 4590
TOTAL