PROJECT REPORT

Website Redesign Project  |  Q3 2024 Status Report

Project Name:  Website Redesign & CMS Migration

Project Manager:  [Your Name]  |  [your.email@company.com]

Report Period:  July 1 - September 30, 2024

Report Date:  [Date]

Status:  ON TRACK  (update to: AT RISK / DELAYED as appropriate)

Budget Consumed:  $[Amount] of $[Total Budget]  ([X]% utilised)

% Complete:  [X]%

1.  EXECUTIVE SUMMARY

The website redesign project is [on track / ahead of schedule / slightly delayed] as of [Report Date]. Key milestones for Q3 have been completed, including [Milestone 1] and [Milestone 2]. The primary risk this quarter was [Risk Description], which was mitigated by [Action Taken]. The project remains within the approved budget of $[Total Budget].

2.  PROJECT BACKGROUND

Objective: Redesign and relaunch the company website to improve user experience, increase conversion rates, and migrate from [Legacy CMS] to [New CMS]. The project was approved on [Approval Date] with a budget of $[Total Budget] and a target go-live date of [Go-Live Date].

3.  PROGRESS SUMMARY

Milestones completed this period:

| Milestone | Due Date | Status | Notes |
| --- | --- | --- | --- |
| Discovery & UX Audit | 15 Jul 2024 | COMPLETE | All 6 audit reports delivered |
| Wireframes Approved | 31 Jul 2024 | COMPLETE | Signed off by stakeholders |
| Visual Design - Desktop | 22 Aug 2024 | COMPLETE | 3 revision rounds |
| Visual Design - Mobile | 5 Sep 2024 | IN PROGRESS | Final review pending |
| CMS Setup & Config | 30 Sep 2024 | IN PROGRESS | 80% complete |
| Content Migration | 15 Oct 2024 | UPCOMING | Scheduled start: 1 Oct |
| UAT & QA | 31 Oct 2024 | UPCOMING |  |
| Go-Live | 15 Nov 2024 | UPCOMING | Target unchanged |

4.  KEY FINDINGS & METRICS

User Research Findings (from UX audit):
  * 68% of users could not locate the contact form within 30 seconds.
  * Mobile bounce rate: 74% (industry average: 55%).
  * [X] user interviews conducted; top pain points: [Pain 1], [Pain 2], [Pain 3].
  * Heatmap: [X]% of clicks on non-interactive elements.

Performance baseline (current site):

| Metric | Current | Target |
| --- | --- | --- |
| Page load time (mobile) | 6.8 s | < 3.0 s |
| Lighthouse Performance Score | 42 / 100 | > 85 / 100 |
| Conversion rate (enquiries) | 0.9% | > 2.5% |
| Average session duration | 1:12 min | > 2:30 min |
| Pages per session | 1.7 | > 3.0 |

5.  RISKS & ISSUES

RISK 1 - Content delivery delay
  Likelihood: Medium  |  Impact: High
  Description: Marketing team has not finalised copy for 12 service pages.
  Mitigation: Escalated to [Name] on [Date]; content deadline extended to [Date].

RISK 2 - Third-party API integration
  Likelihood: Low  |  Impact: Medium
  Description: CRM integration requires API access not yet provisioned.
  Mitigation: IT ticket raised [Date]; estimated resolution [Date].

6.  BUDGET OVERVIEW

| Category | Budgeted | Spent to Date | Remaining |
| --- | --- | --- | --- |
| UX & Design | $18,000 | $17,200 | $800 |
| Development | $40,000 | $22,000 | $18,000 |
| Content & Copywriting | $8,000 | $2,500 | $5,500 |
| QA & Testing | $6,000 | $0 | $6,000 |
| Project Management | $10,000 | $6,750 | $3,250 |
| Contingency (10%) | $8,200 | $0 | $8,200 |
| TOTAL | $90,200 | $48,450 | $41,750 |

7.  RECOMMENDATIONS & NEXT STEPS

1. [APPROVAL NEEDED] Approve revised timeline - go-live moved to [New Date].
2. [ACTION - Project Manager] Chase content team for 12 outstanding service page drafts by [Date].
3. [ACTION - IT] Provision CRM API credentials by [Date].
4. [INFORMATION] Next status report due: [Date]. Steering committee review: [Date].
5. Conduct mid-project retrospective in [Month] to capture learnings for Phase 2.

DISCLAIMER: This template is provided for general informational and drafting purposes only. It does not constitute legal, HR, or professional advice. Consult a qualified professional before relying on this document.