## Project Risk Register
PROJECT RISK REGISTER
Project Name: |  | Project Manager: |  | Version: | Date:
PROBABILITY: 1=Very Low 2=Low 3=Medium 4=High 5=Very High ¦ IMPACT: 1=Negligible 2=Minor 3=Significant 4=Major 5=Catastrophic ¦ Risk Score = P x I
Risk ID | Risk Description | Category | Probability (1-5) | Impact (1-5) | Risk Score (PxI) | Risk Level | Mitigation Strategy | Risk Owner
R-001 | Key stakeholder unavailability delays approvals | Schedule | 3 | 4 |  |  | Appoint deputy decision-maker; escalation path documented | Project Manager
R-002 | Scope creep from unmanaged change requests | Scope | 4 | 3 |  |  | Formal change control board; freeze scope at sprint start | BA / PM
R-003 | Third-party vendor delivery delay | External | 3 | 4 |  |  | Dual-source vendors; contractual SLAs with penalties | Procurement
R-004 | Data migration errors causing data loss | Technical | 3 | 5 |  |  | Full backup pre-migration; parallel run validation; rollback plan | Tech Lead
R-005 | Budget overrun due to underestimated complexity | Financial | 3 | 4 |  |  | 10% contingency reserve; monthly EVM tracking | Sponsor / PM
R-006 | Resource turnover / key person dependency | Resource | 3 | 4 |  |  | Knowledge transfer sessions; cross-training; succession plan | HR / PM
R-007 | Integration failures between new and legacy systems | Technical | 3 | 4 |  |  | Interface testing in staging; API contract tests | Tech Lead
R-008 | Regulatory / compliance requirement changes | Compliance | 2 | 5 |  |  | Monitor regulatory updates; legal review quarterly | Compliance Officer
R-009 | Communication breakdown across distributed teams | Communication | 4 | 2 |  |  | Daily stand-ups; shared Confluence space; RACI matrix | PM
R-010 | User adoption failure post go-live | Benefits | 3 | 4 |  |  | Change management plan; super-users; training programme | Change Manager